|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Monday** | **Tuesday** | **Wednesday** | **Thursday** | **Friday** | **Sat & Sun** |
| **Week 4** | 14-10-2013 | 15-10-2013 | 16-10-2013 | 17-10-2013 | 18-10-2013 | 19/20 - 10 |
|  | Set building main set & puppet making (small characters) | *(Submit VC choice)*  Set building and puppet making continued + schedule and budget. | *Seminar ‘destinations and possibilities’*  Set building and puppet making continued. | Finalizing set (set dressing & lighting) and small puppets, start work on large puppets. | Dope sheets, action analysis, planning shots, prep station for shooting. | (continue preparation for shooting) |
| **Week 5** | 21-10-2013 | 22-10-2013 | 23-10-2013 | 24-10-2013 | 25-10-2013 | 26/27- 10 |
|  | *Foley WS?*  Laura animating shot 1a  Roos working on large scale puppet.  Roos Animating shot 6, laura working on rock set. | Visual culture workshops  Roos animating shot 9,  Laura rock set bulding.  Prep for main wide shot. | Launch of project 2  Laura animating shot 2, Roos finishing large puppet  Start shot 8… (Laura & Roos) | Laura & Roos Animating shot 8. | Laura & Roos Animating shot 10. | Roos finishing large scale puppet, Laura works on dope sheets for next week shooting. |
| **Week 6** | 28-10-2013 | 29-10-2013 | 30-10-2013 | 31-10-2013 | 01-11-2013 | 2/3-11-2013 |
|  | Finishing shot 10 (Laura & Roos)  Taking pictures for all close up backgrounds.  Re-building for greenscreenshots. | Visual culture workshops  *Time for VC & project 2 proposal.* | Tutorials project 2  Laura animating shot 1b & 3  Roos working on sound + edit so far.  *Time for visual culture & proposal.* | Roos animating shot 5, Laura working on rock set.  Laura animating shot 7, Roos working on sound & edit | Roos animating shot 5 & 4,  Laura finishing rock sets + work on project 2 proposal.  Change to rock set if possible. Hand in paper proposal project 2! |  |
| **Week 7** | 04-11-2013 | 05-11-2013 | 06-11-2013 | 07-11-2013 | 08-11-2013 | 9/10-11-2013 |
|  | Change set up for rock set, Laura & Roos animating shot 11. | Visual culture workshops  Laura & Roos animating shot 13.  Change to rock edge set. | Professional practice launch  Laura animating shot 12, Roos sound + edit.  Set up for shot 14, Laura & Roos start animating shot 14 | Laura and Roos finish animating shot 14. | Roos working ong sound & edit, Laura working on wide view set. (or Laura on sound, Roos on set?) |  |
| **Week 8** | Laura or Roos working on wide shot set. Work on sound & post.  Mary workshops! ?? | Visual culture workshops  Photographing wide shot set  Combine with edit. | *Time for last things, catching up, finishing touches.* | *Time for last things, catching up, finishing touches.*  Mary workshops! ?? | *Get film exported, on dvd, etc.*  Mary workshops! ?? | *Work on visual culture draft version!* |
| **Week 9** | Mary workshops! ??  *Visual culture draft version work…* | Submit a 1000 word draft for Visual Culture! | Group film assessment screening!! |  |  |  |