|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Week 6** | 28-10-2013 | 29-10-2013 | 30-10-2013 | 31-10-2013 | 01-11-2013 | 2/3-11-2013 |
|  | Roos animate shot 2  Laura work on shot list, pre-production & schedule | Visual culture workshops  Roos animate shot 8, Laura on paperwork & vis cul | Tutorials project 2  Roos finish shot 8, laura on paperwork and sets.  Laura animate shot 10, Roos on vis cul | Laura finish shot 10, Roos finish big puppet  Roos animate shots 6 & 9  Laura plan for other sets | Hand in paper proposal project 2!Laura animate shot 1  Roos make wooden structures for remaining sets |  |
| **Week 7** | 04-11-2013 | 05-11-2013 | 06-11-2013 | 07-11-2013 | 08-11-2013 | 9/10-11-2013 |
|  | Laura finish shot 1  Roos animate shot 5  Laura set building | Visual culture workshops  Laura animate shot 7  Roos set building | Professional practice launch  Roos animate shot 3 & 4  Laura set building | Roos finish animating shots 3 & 4  Laura set building | Laura animate shot 11  Roos comp |  |
| **Week 8** | Mary workshops! ??  Roos animate shot 12  Laura Work on audio & edit | Visual culture workshops  Laura animate shot 13  Roos comp & edit | Laura finish shot 13  Roos comp, edit & audio | Mary workshops! ??  Roos animate shot 14  Laura edit & bibliograpy | Mary workshops! ??  Roos finish shot 14  Laura edit & bibliography  BURN DISK | *Work on visual culture draft version!* |
| **Week 9** | Mary workshops! ??  *Visual culture draft version* | Submit a 1000 word draft for Visual Culture! | Group film assessment screening! |  |  |  |